## Slide 1: BIOSINT Project Strengthening Capacities and Digital Competences in Biomedical Education through Internationalization at Home BIOSINT final project presentation
Erasmus+ KA2 – Capacity Building in Higher Education Final Project Review Foča, Bosnia and Herzegovina 16–18 December 2025

## Slide 2: AGENDA
Project background
Objectives and structure
Project journey from planning to implementation
Key achievements by work packages
Virtual classrooms and international courses
Impact on students, staff, and institutions
Dissemination, visibility, and sustainability
Lessons learned and next steps

## Slide 3: WHY BIOSINT?
Why was BIOSINT needed?
  Limited international exposure for many WB students
  Mobility opportunities are relatively limited, and not equally accessible to everyone
  Need for modern, digitally supported biomedical education
  Growing importance of Internationalization at Home (IaH)
  Alignment with European Higher Education Area

## Slide 4: BIOSINT CONSORTIUM
Project partnership
  Western Balkan universities
  EU partner institutions
  Ministries and external stakeholders
  Strong balance between experience and regional needs
The strength of BIOSINT lies in its consortium. The project brought together universities from the Western Balkans and the EU, combining academic expertise and experience with an understanding of local educational contexts.

## Slide 5: PROJECT OBJECTIVES
Main objectives of BIOSINT
  Develop institutional IaH strategies
  Strengthen digital and pedagogical competences
  Internationalize existing curricula
  Create and deliver new international virtual courses
  Ensure sustainability and long-term impact

## Slide 6: PROJECT STRUCTURE
BIOSINT Work Packages
  WP1 – PROJECT MANAGEMENT AND QUALITY ARCHITECTURE
  WP2 – RESEARCH AND NEEDS ANALYSIS
  WP3 – DEVELOPMENT OF APPROPRIATE SYSTEM AND PROTOCOL FOR IaH
  WP4 – INTERNATIONALIZATION OF CURRICULUM (IOC)
  WP5 - IMPACT AND DISSEMINATION

## Slide 7: KICK-OFF MEETING, Kragujevac, Serbia, February 23-24 2023

## Slide 8: EU TRAINING MINUTES, Ghent, June 07-09 2023

## Slide 9: EARLY PHASE: ANALYSIS & STRATEGY WORKSHOP IN PODGORICA, June 27-28 2023
Podgorica: Foundations for Success
  Needs analysis conducted at all WB institutions
  Identification of gaps in IaH and digital readiness
  Development and adoption of institutional IaH strategies
WP2 created the foundation for everything that followed. It ensured that BIOSINT activities were not generic but tailored and adapted to institutional needs and national contexts

## Slide 10: EU TRAINING, Vrdnik, Fruška Gora, Serbia, September 21-24 2023

## Slide 11: EU TRAINING, Timisoara, Romania, 17 - 20 OCTOBER 2023

## Slide 12: MOSTAR MEETING & ACTIVITIES WORKSHOP IN MOSTAR, April 3-5 2024
The following topics were addressed:
  Guidelines for Incoming Students and Staff
  Safety and Security Policy
  Establishment of Buddy System
Proposals: Written documents for each topic to be developed and
formalized across the consortium.
Consortium Board Meeting:
  Review of the project status, financial planning, and equipment purchases.
  Coordination of activities for the follow up meeting in Shkodra

## Slide 13: WORKSHOP IoC IN SKHODRA, October 8-11 2024
Presentations on curriculum internationalization by
  Geert De Lepeleer, Nenad Markovic and Ljiljana Tasic
Selection of existing courses for IaH.
Developing strategies for integrating intercultural competencies into curricula.
Models for International Collaboration:
  COIL/CLIL/TILT/EMI teaching methods presented by Nenad Markovic.

## Slide 14: WORKSHOP IN TUZLA, December 4-6 2024
Course Development and Piloting:
  Selection of existing courses for IaH.
  Pilot virtual classrooms planned for March-June 2025.
Digital Protocols:
  Institutional training and buddy system documentation completion.
  Challenges in Albania due to study program updates.
Deliverable Deadlines and Challenges:
  Submit missing documents
  Deadline extentions
Dissemination Plans:
  Website development by UMT & UES.
  Six newsletters from UNISHK, two completed.
  Research papers on IaH challenges and Buddy system

## Slide 15: CONSORTIUM MEETING, Tirana, June 4-5, 2025
High-level institutional and ministerial participation
Review of achievements across all WPs
Media coverage (RTSH, Euronews Albania)
Recognition of BIOSINT as a good practice
The Tirana meeting represented both a milestone and a validation of the project’s relevance and impact
T4.5. Strengthening of online teaching platform/ equipment – development international virtual classroom
D. 4.5 Virtual Classroom

## Slide 16: CAPACITY BUILDING FOR TEACHERS
Training academic staff
  International pedagogy and IaH concepts
  Digital teaching methods
  Intercultural competence
  English language proficiency
A major success factor of BIOSINT was investing in people.

## Slide 17: TRAINING OVERVIEW
KU Leuven Ghent Campus (June 2023)
  Internationalization strategies at KU Leuven and lab visits
  Internationalization at Home, collaborative research projects, and curriculum integration
BIOSINT Training at Educons University Center in Vrdnik (Sept. 2023)
  Integration of knowledge and skills for IaH in biomedical education
  Innovative approaches in research, interdisciplinary learning, and developing joint projects
Victor Babes University Timisoara (Oct. 2023)
  Internationalization practices and research-driven education at Victor Babes University
  Doctoral education, research integration, and internationalization strategies for medical and biomedical sciences

## Slide 18: Key Outcomes from the Trainings
All participants gained deeper insights into how internationalization can be used and implemented within biomedical education programs at different institutions.
Focus on shared research interests such as affordable medical technologies and healthcare innovations, strengthening future research partnerships.
Sharing of best practices for integrating international perspectives into curricula, fostering a more interdisciplinary, collaborative educational environment.
Strengthened connections between universities from the Western Balkans and EU institutions through shared workshops, lab visits, and creative dialogues.

## Slide 19: On-line Teacher Training, December 2024
Focus on international curriculum design
Practical recommendations from EU partners
Strong interaction and discussion
Teachers’ competence in Biomedical education – international approach
Prof. dr Ljiljana Tasić, UniKG
2. How to internationalize the curriculum: practical recommendations for teachers from a holistic point of view
Geert De Lepeleer, KU Leuven

## Slide 20: OVERCOMING CHALLENGES
How we responded
  Parallel implementation of activities
  Regular online coordination meetings
  Adjusted timelines without reducing scope
  Strong leadership and partner commitment

## Slide 21: CHALLENGES ENCOUNTERED
Challenges during implementation
  Procurement delays for virtual classroom equipment
  Administrative and accreditation procedures
  Different national regulations
  Coordination across multiple institutions
As with many international projects, BIOSINT faced challenges. The important part is that these challenges were anticipated, monitored, and addressed collaboratively.

## Slide 22: FROM PLANNING TO DELIVERY
Transition to full implementation (2025)
  Adoption of new courses at institutional councils
  Allocation of teachers and students
  Platform alignment (Microsoft Teams)
  Launch of virtual classrooms
This phase was a critical milestone for us — BIOSINT moved from preparation into real educational territory

## Slide 23: INTERNATIONAL VIRTUAL COURSES
Three new international courses
  Medical Nutritional Therapy
  Personalized Medicine
  Health Management in Crisis
Key characteristics:
  15 weeks per course
  International teaching teams
  COIL and IaH models
  Digital assessment and certification
These courses are the core educational output of BIOSINT and a concrete example of Internationalization at Home in action

## Slide 24: STUDENT PARTICIPATION & FEEDBACK
Student engagement
  300+ students per course
  High attendance and completion rates
  Positive feedback on the experience
  Appreciation of mobility-at-home

## Slide 25
Foca
Mostar
Podgorica
Shkodra
Tirana
Tuzla
Timisoara

## Slide 26: IMPACT ON INSTITUTIONS
Institutional impact
  Strengthened digital infrastructure
  Improved readiness for accreditation
  Institutionalization of IaH strategies
  Enhanced international cooperation

## Slide 27: DISSEMINATION & VISIBILITY
Websites (https://biosint.net/) and social media
Newsletters and info days
Round tables and stakeholder meetings
Scientific publications in preparation
Dissemination ensured that BIOSINT’s results reached not only project partners, but also policymakers, academics, and the wider public
@_biosint_

## Slide 28: SCIENTIFIC OUTPUTS
Research and publications
  Joint scientific paper
  Planned second paper related to Buddy System
  Contribution to international academic discourse in general

## Slide 29: SUSTAINABILITY
Beyond the project
The possibilities of:
  Continued delivery of virtual courses
  Integration into regular curricula
  Strengthened EU–WB partnerships
  Foundation for future Erasmus+ projects

## Slide 30: KEY LESSONS LEARNED
What we learned
  Internationalization works best when inclusive
  Digital tools enable, but people are those who ensure success
  Strong coordination is essential
  Flexibility makes success possible

## Slide 31: CONCLUSION
A successful transformation of biomedical education through Internationalization at Home, digital innovation, and strong partnership.

## Slide 32
Thank You for Your Attention
Questions & Discussion

## Slide 33: Disclaimer and Acknowledgement
Project number: 101082863-BIOSINT-ERASMUS-EDU-2022-CBHE
Funded by the European Union. Views and opinions expressed are however those of the author(s) only and do not necessarily reflect those of the European Union or European Education and Culture Executive Agency (EACEA). Neither the European Union nor the granting authority can be held responsible for them.