## Slide 1: Ongoing/ planned activities and difficulties E1.3 CONSORTIUM MEETING TIRANA/ 4.2 INT’L OF CURRICULUM
University of East Sarajevo Faculty of Medicine Foča
Prof. dr Nenad Markovic
Doc. dr Radmila Balaban Đurević
Prof. Minja Ćosović
University of Medicine Faculty of Dentristry Tirana
3-6. June 2025.

## Slide 2
It must be emphasized that internationalization is not a goal in itself.
Rather, it is a mean of improving quality that, if implemented successfully, not only improves the overall study quality at the University, but also grows the University’s reputation in the international higher education sphere.

## Slide 3: The key ongoing activity?
Waiting for the international accreditation by WFME
In 2024 we developed of the SER and submitted it in September 2024.
WFME standards. One standard one team. 8 standards.
In January we had 2 online meetings and 1 f2f meeting in Foča.
In May we got information about possible suggestion about Commission report.

## Slide 4: WP1 - Project management and quality architecture
T1.3 Organizing consortium meetings - Tirana? Foča?
T1.5 Internal and external quality progress reporting – continuous activity until the end of project duration
T1.7 Organizing of reporting to EACEA – final report in Sygma
T1.8 Evaluation of meetings via survey – until the end.
T1.9 Financial and administrative management – continuous.

## Slide 5: WP1 - Project management and quality architecture
MS4 Percent of realized activities in quality reporting
T1.1 Signing of Quality policy statement
T1.2 Establishing of the project organizational structure
T1.3 Organizing consortium meetings
T1.4 Development of project management and quality strategies
T1.5 Internal and external quality progress reporting
T1.6 Organization of external monitoring visit
T1.7 Organizing of reporting to EACEA
T1.8 Evaluation of meetings via survey
T1.9 Financial and administrative management
100%
100%
66,6%
100%
66,6%
100%
50%
80%
50%
79,2% TOTAL

## Slide 6: WP1 - Project management and quality architecture
MS4 Percent of realized activities in quality reporting
50%
66,6%
100%
100%
79,15% TOTAL
D1.1 Interim and final report
D1.2 Internal and external quality reports
D1.3 Consortium agreement
D1.4 Project management handbook

## Slide 7: WP2 – Research and needs analysis
T2.1 Analyse the situation of IaH in the EU
T2.2 Analyse the situation of IaH at WB partners
T2.3 Framework development for IaH at WB universities
T2.4 Organize trainings at EU partners
100%
100%
100%
100%
100% TOTAL
D2.1 IaH need based reports
D2.2 Framework map road of IaH
D2.3 EU trainings
100%
100%
100%
100% TOTAL
MS6 Detailed and informative reports on IaH – number of case studies, number of reports, number of pages in each report
MS7 Transparent framework map – number of elements in the framework map

## Slide 8: WP3 – Development of appropriate system and protocol for IaH
T3.1 Printing strategies – 2000 EUR
T3.5 Pilot newly developed services and docs - Each WB partner will pre-test newly developed documents, strategy, support and safety protocols, guidelines, buddy system and put all these into action. In the 1st project year, all these will be developed and in the 2nd project year will be tested.
International cooperation | Faculty of Medicine Foca - Studies in English
T3.6 Evaluate of pilot activities - Students, staff and external stakeholders will evaluate all piloted activities through electronic questionnaire.

## Slide 9: WP3 – Development of appropriate system and protocol for IaH
1. Are you satisfied with the International cooperation register at the link https://studiesinenglish.mef.ues.rs.ba/# ?
yes no I don’t know
2. Do you have any suggestion for addition in the sense that this register should include some additional element?
Yes (Specify which) No
3. Do you think that the buddy system can integrate newly arrived students adequately?
yes no
4. Do you have any suggestions for improving international cooperation at the Faculty of Medicine?
Yes (Indicate your suggestion) No

## Slide 10: WP3 – Development of appropriate system and protocol for IaH
100%
100%
100%
100%
100%
0%
83,3% TOTAL
100%
100%
100%
100%
100% TOTAL
MS8 Adopted strategies for IaH at WB HEIs – number of adopted strategies for IaH, average number of pages in one strategy
MS9 Functional and tested digital services and protocols – number of digital services and protocols average in one WB HEIs
MS10 – Well trained staff and students from biomedical HEIs – number of educated students, staff and external stakeholder per one biomedical WB HEI
D3.1 Strategies for IaH at WB HEIs
D3.2 Institutional trainings
D3.3 Digital protocols for international students and staff
D3.4 Buddy systems
T3.1 Develop strategies for IaH at WB HEIs
T3.2 Organize starting training for students and staff
T3.3 Develop digital support system and protocol for international students and staff
T3.4 Institutional trainings for internal and external stakeholders
T3.5 Pilot newly developed services and documents
T3.6 Evaluate of pilot activities

## Slide 11: WP4 – Internationalization of curriculum (IoC)
T4.1 Development of intercultural competences – 5 teachers finished the course in duration of 3 months and got certificates.
T4.6 Piloting courses for IoC/ COIL for virtual international courses - Internationalized syllabuses within T4.2 and virtual courses within T4.4 will be piloted/ implemented in practice. Participant lists. Teacher reports. Printing certificates to students (DESIGN) – until the middle of June 2025.
T4.7 Evaluate of pilot activities - Target groups will be evaluated through questionnaire in order to collect opinions – create of questionnaire and finish the activity until the end of June.

## Slide 12: WP4 – Internationalization of curriculum (IoC)
T4.1 Organize workshops for teaching staff related to IoC and development of intercultural competences
T4.2 Select courses for IoC and review current practices
T4.3 Establish models for connection with international students and staff (COIL/ CLIL/ TILT/ EMI)
T4.4 Develop new international virtual courses
T4.5 Strengthening of online teaching platform/ equipment - development international virtual classroom
T4.6 Piloting courses for IoC/ COIL for virtual international courses
T4.7 Evaluation of pilot activities
D4.1 Trainings for teachers in IoC
D4.2 Internationalized existing courses
D4.3 New developed international virtual courses
D4.4 Equipment for digital online teaching platform
D4.5 Virtual classrooms
100%
100%
100%
100%
100%
80%
0%
82,8% TOTAL
100%
100%
100%
100%
100%
100% TOTAL

## Slide 13: WP5 – Impact and dissemination
T5.2 Making tools for dissemination – press releases (dissemination conference in Foča). Printing diss material (3000 EUR). Promo video (1000-1500 EUR). Scientific work?
T5.3 Raising awareness through info-days, symposia and conferences (1 info day, 1 round table, 1 workshop). Organization of diss. conf. (1550 EUR = ?).
T5.4 Preparation of the interim and final report on dissemination and exploitation activities - (Sygma system – diss. activity).
T5.5 Reporting on impact and sustainability – success stories by all partners.

## Slide 14: WP5 – Impact and dissemination
40%
100%
0%
0%
0%
28% TOTAL
100%
0%
00%
33,3% TOTAL
MS15 Report on impact and sustainability – number of meetings per partners, number of suvvess stories, number of expoitation activities/ sustainability plan by each partner - ?
T5.1 Design and implementation of dissemination and exploitation plan
T5.2 Making tools for dissemination
T5.3 Raising awareness through info-days, symposia and conferences
T5.4 Preparation of the interim and final report on dissemination and exploitation activities
T5.5 Reporting on impact and sustainability
D5.1 Dissemination and exploitation plan
D5.2 Website with report
D5.3 Sustainability action plan