## Slide 1: UNTZ: Overview of Ongoing and Planned Activities and Institutional Challenges
Erasmus+ KA2 Capacity Building in the field of Higher Education
Strengthening capacities and digital competences in biomedical education through internationalization at home – BIOSINT
101082863-BIOSINT-ERASMUS-EDU-2022-CBHE
Tirana, 2025
Dr Kavgić Dalila
Dr Mujaković Elma

## Slide 2: Work Package 1 – WP1
T1.8 - Evaluation of meetings via onsite/online surveys
Surveys completed
T1.9 - Financial and administrative management
Key actions:
Bank account established and installments received
Procurement initiated for virtual classroom
Travel costs processed
Minutes, attendance lists and photos compiled

## Slide 3: Work Package 3 – WP3
T 3.1 Development of strategies for IaH by WB Institutions
Internationalization Strategy (2024–2029) developed and approved
T 3.2. Training for students and staff
4th EU Training (Mostar, April 2024)

## Slide 4: Work Package 3 – WP3
T3.3: Digital support system developed
Guide for incoming students and staff
Safety and Security Protocol for the international students and staff
The Buddy System

## Slide 5: Work Package 3 – WP3
T 3.4 Institutional trainings for internal and external stakeholders
Trainings held for 130 students and staff
T3.5 & T3.6: Pilot activities and evaluations
in progress
Institutional Training (Tuzla, December 2024)

## Slide 6: Work Package 4 – WP4
T 4.1 Workshop for teaching staff related to IoC and development of intercultural competences
T 4.1 Workshop on IoC held in Shkoder
(October,2024)

## Slide 7: Work Package 4 – WP4
T4.2: 30 ECTS worth of courses internationalized
Special Health Care – 6 ECTS
Special Methods in Medical Laboratory
Diagnostics – 6 ECTS
Special Physiotherapy Methods – 6 ECTS
Special Radiological Methods – 6 ECTS
Special Sanitary Health Methods – 6 ECTS
Consent for the alignment of study programs (February, 2025)

## Slide 8: Work Package 4 – WP4
T 4.5 Development of international virtual classroom
Equipment purchased and installed
Procurement managed per BiH Public Procurement Law
Contract awarded to NEONETEX d.o.o. Tuzla
Equipment installed at the Faculty of Medicine
(February, 2025)

## Slide 9: Work Package 4 – WP4
T 4.4 New international virtual courses
Medical Nutritional Therapy
Health Management in Crisis
Personalised Medicine
Personalised medicine (28.05.2025.)

## Slide 10: Upcoming steps
English Language Course for Teaching Staff – Proficiency Assessment and Continued Improvement
Evaluation of pilot activities (T 4.7)
Raising awareness  info-day, round table, workshop (T 5.3)

## Slide 11: Institutional Challenges
Administrative and bureaucratic delays
  💡 Possible Mitigation: Advocate for simplified internal procedures for EU-funded projects. Designate project-specific liaison officers at the university to speed up documentation flow.
Complex procurement procedures under national law
  💡 Possible Mitigation: Plan procurement activities well in advance with buffer periods. Develop procurement templates and commission plans early in the project cycle.
Limited availability of staff for additional tasks
  💡 Possible Mitigation: Offer formal workload recognition or incentives for participation in BIOSINT activities. Encourage team-based work to distribute responsibilities more equitably.

## Slide 12: Conclusion and Final Remarks
UNTZ remains committed to BIOSINT objectives
Key achievements: improved infrastructure, revised curricula, enhanced training
Focus ahead: pilot activities, awareness-raising, virtual courses
Thank you to our partners and the EU for their continuous support

## Slide 13: THANK YOU FOR YOUR ATTENTION